## Sheet1
Machine Site Prep Checklist
| Item Description | Required | Received | Source | % Complete | Ball In Court | Issue
Stuctural and Architectural Information
Cabinet Dimensions
Cabinet Weights
Cabinet Weight Dispersion
Cabinet Quantity
Cabinet Openings for Isobase Coordination
Cabinet Layout
System Layout
Cabinet service clearances required (front, back, sides, top & bottom)
Logistics: Packaging/shipping details (e.g. racks fully loaded, or contents shipped separately; number of pallets, number and dimensions of trucks per delivery)
Electrical Information
Maximum power draw per cabinet
Minimum power draw per cabinet
Average power draw per cabinet
Connection information for racks (Hard wired vs. receptacle; location and length of power cords)
Number of Branch Circuits
Current
Voltage
Number of Phases
Total system electrical performance - Max. MW
Typical system electrical performance - MW
Total system electrical performance - Idle MW
Total system electrical performance - Benchmark MW
Load characteristics per rack (Harmonic projections)
Power redundancy capabilities (e.g., ability to handle loss of single connection)
Circuit synchronization limitations or requirements per cabinet
Inter-rack Cable Distribution (overhead, underfloor, etc) - Cable tray requirements
Rack AC-DC conversion drawings for efficiencies
Mechanical Information
Total typcial heat in tons both liquid and heat
Air - Typical heat to air in for the system(tons)
Air - typical heat to air for the system (MW)
Air - CFM for the system
Liquid - Typical heat to to liquid for the system (tons)
Liquid - Typical heat to liquid for the system (MW)
Location of air flow per cabinet (side, bottom and top, inlet and exhaust requirements
Air - Typical heat for the rack (tons)
Air - typical heat to air for the rack (kW)
Minium air flow rate per cabinet
Maximum air flow rate per cabinet
Air CFM Benchmark
Maximum allowable water flow rate through the cabinet
Minimum air inlet temperature
Maximum air inlet temperature
% of water to % of air at worst case vs idle
Water flow and inlet temperature curves for 100% heat removal per cabinets at idle
Water side pressure drop vs flow between connection points - Cv
Liquid - Typical heat to liquid for the rack (kW)
Liquid - Typical heat to to liquid for the rack (tons)
Liquid - Required inlet temperature
GPM per rack
PSI per rack
Water connections - type and quantity
Allowable cooling fluid flow and temperature excursion magnitudes and durations
Wetted materials within the cabinet
Piping requirements - Copper, Stainless, Polyproplene?
Heat/cold containment measures or requirements
Vibration Limitations
Maximum and minimum operating temperature
Maximum and minimum operating humidity
Controls Information
Telemetry available per node or rack
System self-protection features
Flow control at racks
Water quality information
pH
Conductivity, µmho
P-Alkalinity, as CaCO3, mg/L
M-Alkalinity, as CaCO3, mg/L
Calcium Hardness, as CaCO3, mg/L
Magnesium Hardness, as CaCO3, mg/L
Iron, as Fe, mg/L
Total Iron, as Fe, mg/L
Copper, as Cu, mg/L
Total Copper, as Cu, mg/L
Zinc, as Zn, mg/L
Sodium, as Na, mg/L
Potassium, as K, mg/L
Chloride, as Cl, mg/L
Sulfate, as SO4, mg/L
Nitrate, as NO3, mg/L
Ortho-Phosphate, as PO4, mg/L
Silica, as SiO2, mg/L
Aluminum, as Al, mg/L
Ammonia, as NH3, mg/L
Boron, as B, mg/L
Molybdenum, as Mo, mg/L
Lead, as Pb, mg/L
Tin, as Sn, mg/L
Titanium, as Ti, mg/L
Silver, as Ag, mg/L
Total Azole, mg/L
Fluoride, as F, mg/L
Oil & Grease, mg/L
Total Organic Carbon, mg/L (includes biocide contribution)
Turbidity, as NTU
System Administration and Operation Information
Expected system resource utilization
Will power management be utilized?
Will any power limiting measures be utilized?
Demand limiting?
What is the electrical swing of the entire machine from peak to idle?
Can the rate of ramping from idle to normal/max be controlled?
How is the system partitioned upon loss of power in relation to cooling level? Entire machine or by row or by rack?
Will any data analytics be used to gather power usage profile data based on job schedule?
Will there be a method of communication between the HPC system and the facilities power and cooling systems?
Granularity of rack enviornmental information (per second, etc)
Cabinet/system fire protection requirements (e.g. Inergen, Vesda, etc.)